Team Charter

1 Team vision

We aim to help university students keep track of course notices, assignments and deadlines across WeChat groups, learning platforms, emails and classroom announcements, and identify what needs attention next.

2 Members and responsibilities

| Member | Relevant skills to confirm | Primary responsibilities |
| --- | --- | --- |
| 陈沫含 | Task planning; team coordination; needs elicitation; system design | Coordinate tasks; maintain the project index; lead documentation and presentation. Review research records. |
| 邓雨彤 | Interviewing; documentation; file management; UI design | Study users’ needs; lead interviews and evidence synthesis. Review design against user findings. |
| 田孜乐 | Interaction analysis and design; UI prototyping; presentation | Lead presentations, task priorities and reminders; lead UI prototypes and visuals. Review final layout and links. |

Roles may rotate. All members contribute across stages; someone other than the author reviews each major deliverable.

3 Norms and accountability

1. Communication: Use WeChat; acknowledge messages within 24 hours and flag urgent issues.

2. Meetings: Meet Friday at 12:30 for 30-60 minutes. Update the shared task board beforehand; report absence in advance.

3. Task ownership: Record an owner, due date and expected output for each task. Review workload weekly and redistribute work fairly.

4. Blockers: Report risks before the deadline, explain the blocker, and propose a revised plan. Record any agreed change of owner, scope or due date.

5. Missed commitments: Contact the owner within 24 hours, agree a recovery plan, and record it. Discuss repeated missed commitments and adjust responsibilities.

6. Decisions and conflict: Seek consensus using evidence; otherwise use a 2-of-3 vote and record the rationale. Escalate unresolved workload or conduct disputes to the TA after 48 hours.

7. Quality and integrity: Finish drafts 48 hours before submission; a peer checks the rubric and evidence. Record actual contributions and substantive AI use separately; exclude identifiable participant data from submissions.

4 Information and document management

Workspace: Use a shared Github project named HCI. The Project_Index document is authoritative and links to the task board and current reviewed files. Shared-space link: [5425-dyt/HCI: HCI大作业].

Folder outline: 01_Research / 02_Meetings / 03_Decisions / 04_Design / 05_Submissions. Store each record in its corresponding folder. As the project progresses, the folder outline will become more detailed.

Versions: Example: P0_TeamCharter_v01_20261007.docx. Use platform version history and a short change log.

Updates: The rotating meeting recorder posts minutes within 24 hours. chenmohan updates decisions, reasons and assignments within 24 hours; dengyutong logs research sources on the day collected; tianzile updates design links after each revision. Before submission, all members test access and locate reviewed files.